## ProjectTeam
Name | GitHub Alias | Role
Florian | monkeyinabox | Mule
Ali | Aleistar Markóczy | Minion
Rolf | RolfZurbrugg | Minion
Adrian | Adrian Aulbach | Minion
Samuel | eggsa | Scum Master

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Patient Management | Possiblility to add, modify, view and delete Patients. Providing Users in ER patient information to determine diagnose, current medication and personal or patient risks | high | 34 |  |  | UI Ready needs extension, Logic started, overall 75%
2 | User Authentication and Management | User Access Control to meet legal norms in regards of how can access data | low | 32 |  |  | UI Ready, bakend connection nyi, overall 50%
3 | Transfering Patient | Ability to manage different Clinics and assigne responisble doctors to patients | medium | 32 |  |  | Not started
4 | Documenting Patient Sessions | Provide ability to collect Patient records in a history and write new reports during an ongoing Session with a patient | high | 32 |  |  | Not started
5 | Time and Event Management | Providing timetables for doctors to know their daily tasks as well as an overview of all doctors assigned to a clinic. Setup session and assign doctors an patients | high | 60 |  |  | Not started
6 | Prescritption Management | Checking prescritions dosage and reciprocation | low | 80 |  |  | Not started
|  |  |  | 270 | 150

## Sprint Backlog S1
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Implement UI structure | Menu and General UI component | UI | Ali/Adrian | Florian | medium | 12 |  | 4 | Done | 12
1.4 | 1 | Patient view | Patient overview, showing current medication and risks to self an others | UI/view | Adrian | Rolf | high | 8 |  |  | Open | 0
1.2 | 1 | Basic Hibernate setup | Database PoC, basic hibernate implementation | Database | Samuel | Florian | low | 8 |  |  | Open | 0
1.3 | 1 | Manage patient | Implenment Service and Class, providing a template for all future implementations | Model, Services | Samuel | Rolf | medium | 4 |  | 3 | Open | 0
0.1 | 1 | Basic project setup | Create empty packages/classes etc… | Implementation | All | All | high | 2 |  | 1 | Done | 2
1.4 | 1 | General UI Layout | Vaadin layout definition | UI | Ali/Adrian | Florian | high | 8 |  | 4 | Done | 8
2.1 | 1 | User Authentication | User Access Control, possibility to authenticate as a user | Model | Rolf | Ali | low | 4 |  |  | Open | 0
2.2 | 2 | Manage Users | Implement Service and Class for users | Access Control | Rolf | Ali | low | 8 |  |  | Open | 0
[11 empty] | Total Sprint 1 | 22

## Sprint Backlog S2
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
Left over from Sprint 1
1.4 | 2 | Patient view | Patient overview, showing current medication and risks to self an others | UI/view | Adrian | Rolf | high | 8 | 8 |  | Open | 0
1.2 | 2 | Basic Hibernate setup | Database PoC, basic hibernate implementation | Database | Samuel | Florian | low | 8 | 8 | 6 | Done | 8
1.3 | 2 | Manage patient | Implenment Service and Class, providing a template for all future implementations | Model, Services | Samuel | Rolf | medium | 4 | 4 | 4 | Done | 4
New Features Sprint 2
2.1 | 2 | User Authentication | Encyption and persistence of passwords | Model | Rolf | Ali | low | 4 | 4 | 5 | Done | 4
2.2 | 2 | Manage Users | Implement Service and Class for users | Access Control | Rolf | Ali | low | 8 | 8 |  | Done | 8
2.3 | 2 | Domain Model | All persistent data as chart and implemented (Task 12, due 26.05.17) | Persistence | All | All | high | 16 | 16 | 16 | Done | 16
2.4 | 2 | Patient states | Billing (State Machine) Core-functionality only | Billing | Adrian | Samuel | high (task) | 8 | 8 | 12 | Done | 8
2.5 | 2 | Main View redesign | Buttons by graphics, Buttons on top, Mobile ability | UI/view | Ali | Adrian | high | 4 | 4 | 5 | Done | 4
2.6 | 2 | Patient Search | Implement View, Filtering request (XML/JSON), load to patient view | UI/view/db | Ali/Rolf | Adrian | low | 8 | 8 |  | Open | 0
2.7 | 2 | Session Management | Session specific UI elements and other constants on user login | Access Control | Ali | Samuel | medium | 2 | 3 | 3 | Done | 2
2.8 | 2 | Timetable | Basic View and implementation: Add Event / Session, overview | UI/view | Ali | Samuel | medium | 8 | 8 |  | Open | 0
2.9 | 2 | Timetable | Services add, remove, filter operations | Database | Samuel | Florian | medium | 4 | 4 |  | Open | 0
2.10 | 2 | Path Params | Navigation with path parameters | Navigation | Ali | Rolf | high | 4 | 4 | 3 | Done | 4
[7 empty] | Total | 86 |  |  | Total | 58

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2017-05-02 | 270 | 270
1 | 2017-05-11 | 248 | 233 | Sprint 1: 7 h. p.P.