## Slide 1: MHC PMS Task10
Gruppe Rot

## Slide 2: Übersicht
Sprint Analyse
Fazit
(Vorführung)

## Slide 3: Sprint Analyse
Sprint Backlog
scrum_v02.xlsx
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Implement UI structure | Menu and General UI component | UI | Ali/Adrian | Florian | medium | 12 |  | 4 | Done
1.4 | 1 | Patient view | Patient overview, showing current medication and risks to self an others | UI/view | Adrian | Rolf | high | 8 |  | 6 | Open?
1.2 | 1 | Basic Hibernate setup | Database PoC, basic hibernate implementation | Database | Samuel | Florian | low | 8 |  | 3 | Done
1.3 | 1 | Manage patient | Implenment Service and Class, providing a template for all future implementations | Model, Services | Samuel | Rolf | medium | 4 |  | - | Partially Done (80%)
0.1 | 1 | Basic project setup | Create empty packages/classes etc… | Implementation | All | All | high | 2 |  | 1 | Done
1.4 | 1 | General UI Layout | Vaadin layout definition | UI | Ali/Adrian | Florian | high | 8 |  | 4 | Done
2.1 | 1 | User Authentication | User Access Control, possibility to authenticate as a user | Model | Rolf | Ali | low | 4 |  | 2 | Done
2.2 | 2 | Manage Users | Implement Service and Class for users | Access Control | Rolf | Ali | low | 8 |  | 4 | Open

## Slide 4: Sprint Analyse
Burndown Chart
Chart: Burndown Chart
| 42857 | 42866
Remaining Effort | 270 | 235
Remaining Resources | 270 | 236
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 02.05.2017 | 270 | 270
1 | 11.05.2017 | 235 | 236

## Slide 5: Fazit
Fast alle Ziele erreicht, ausstehende Ziele aus Sprint 1 jedoch erledigtes aus Sprint 2.
Wenig Kapazität, Ausgleich durch zu hohe Einschätzung
Erste lauffähige Version erstellt

## Slide 6: Vorführung
MHC PMS Red