## ProjectTeam
Name | GitHub Alias
Florian | arsch1
Ali | arsch2
Rolf | arsch3
Adrian | arsch4
Samuel | arsch5 | ScumMasterer

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Patient Management | Possiblility to add, modify, view and delete Patients. Providing Users in ER patient information to determine diagnose, current medication and personal or patient risks | high | 34
2 | User Authentication and Management | User Access Control to meet legal norms in regards of how can access data | low | 32
3 | Transfering Patient | Ability to manage different Clinics and assigne responisble doctors to patients | medium | 32
4 | Documenting Patient Sessions | Provide ability to collect Patient records in a history and write new reports during an ongoing Session with a patient | high | 32
5 | Time and Event Management | Providing timetables for doctors to know their daily tasks as well as an overview of all doctors assigned to a clinic. Setup session and assign doctors an patients | high | 60
6 | Prescritption Management | Checking prescritions dosage and reciprocation | low | 80
|  |  |  | 270 | 150

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Design reusable UI Components | Menu and Mockups | UI | Ali, Samuel | Adrian | medium | 12 |  |  | Open
1.2 | 1 | Basic Hibernate setup | Database PoC | Database | Florian, Rolf | Samuel | low | 8 |  |  | Open
1.3 | 1 | manage Patient | Implenment Service and Class | Model, Services | Florian | Rolf | high | 4 |  |  | Open
1.4 | 1 | basic project setup | Create empty packages/classes etc… | Implementation | Samuel | Ali | high | 2 |  |  | Open
1.5 | 1 | General UI Layout | Vaadin layout definition | UI | Rolf | Adrian | high | 8 |  |  | Open
1.6 | 1 | User Authentication | User Access Control | Model | Adrian | Florian | low | 4 |  |  | Open

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180