## ProjectTeam
Name | GitHub Alias | Role
Florian | monkeyinabox | Mule
Ali | Aleistar Markóczy | Minion
Rolf | RolfZurbrugg | Minion
Adrian | Adrian Aulbach | Minion
Samuel | eggsa | Scum Master

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Patient Management | Possiblility to add, modify, view and delete Patients. Providing Users in ER patient information to determine diagnose, current medication and personal or patient risks | high | 34
2 | User Authentication and Management | User Access Control to meet legal norms in regards of how can access data | low | 32
3 | Transfering Patient | Ability to manage different Clinics and assigne responisble doctors to patients | medium | 32
4 | Documenting Patient Sessions | Provide ability to collect Patient records in a history and write new reports during an ongoing Session with a patient | high | 32
5 | Time and Event Management | Providing timetables for doctors to know their daily tasks as well as an overview of all doctors assigned to a clinic. Setup session and assign doctors an patients | high | 60
6 | Prescritption Management | Checking prescritions dosage and reciprocation | low | 80
|  |  |  | 270 | 150

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Implement UI structure | Menu and General UI component | UI | Ali/Adrian | Florian | medium | 12 |  |  | Open
1.4 | 1 | Patient view | Patient overview, showing current medication and risks to self an others | UI/view | Adrian | Rolf | high | 8 |  |  | Open
1.2 | 1 | Basic Hibernate setup | Database PoC, basic hibernate implementation | Database | Samuel | Florian | low | 8 |  |  | Open
1.3 | 1 | Manage patient | Implenment Service and Class, providing a template for all future implementations | Model, Services | Samuel | Rolf | medium | 4 |  |  | Open
0.1 | 1 | Basic project setup | Create empty packages/classes etc… | Implementation | All | All | high | 2 |  |  | Open
1.4 | 1 | General UI Layout | Vaadin layout definition | UI | Ali/Adrian | Florian | high | 8 |  |  | Open
2.1 | 1 | User Authentication | User Access Control, possibility to authenticate as a user | Model | Rolf | Ali | low | 4 |  |  | Open
2.2 | 2 | Manage Users | Implement Service and Class for users | Access Control | Rolf | Ali | low | 8 |  |  | Open

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180